# Basis of Schedule

Tender for :

Prepared by :

Dated :

Contents

1.	Executive Summary

1.1	Client & Project Information	3

1.2	Key Milestones:	3

1.3	Key Assumptions	3

1.4	Key Production Rates	3

1.5	Risks & Opportunities	4

1.6	Summary Program	4

2.	Project Summary	5

2.1	Location Map	5

2.2	Scope of Works	5

2.3	Program Overview / Strategy	5

2.4	Project Specific Issues	5

3.	Program Details	6

3.1	Location & Identification	6

3.2	General Settings in P6	6

3.3	Work Breakdown Structure	6

3.4	Calendars.	6

3.5	Allowable Working Hours.	6

3.6	Design	6

3.7	Procurement	6

3.8	Construction Methodology	6

4.	Key Assumptions	7

4.1	Site Access and Establishments	7

4.2	Productivities	7

5.	Overall Labour Histogram	7

6.	Critical Path.	8

7.	Relevant Project Benchmarking	8

8.	Inclement Weather Analysis	8

9.	Schedule Risk Analysis	8

10.	Contingency	8

Appendix A – Summary Programme	9

Appendix B – Inclement Weather Analysis	9

Appendix C - Schedule Risk Analysis	9

Appendix D – Project Calendars	9

Appendix E – Critical Path	9

Appendix F – Contractual Requirement Relevant to ‘Planning/Programming/Time’	9

Appendix G - Table of Productivities	9

Appendix H– Schedule Quality Checks	9

Appendix I – Work Breakdown Structure (Level 4)	9

# Executive Summary

(note this section to be presented for tender review purposes)

## Client & Project Information

| Project Name | (input) |
| --- | --- |
| Location | (input) |
| Client | (input) |

## Key Milestones:

|  | Key Dates | Weeks |
| --- | --- | --- |
| Tender Submission Date: | (input) |  |
| Tender Validity Period: | (input) | (input) |
| Contract Award: | (input) |  |
| Construction Commencement: (Add/Delete as req’d) | (input) |  |
| Milestones / Separable Parts Completion: |  |  |
| - Milestone/SP # 1 |  |  |
| - Milestone/SP # 2 |  |  |
|  |  | Weeks |
| Contract Date for Practical Completion: | (input) | (input) |
| Target (Net) Completion Date: | (input) | (input) |
| SRA P70 Completion Date: | (input) | (input) |
| Forecast (Gross) Completion Date: | (input) | (input) |
| Defects Liability Period: | (input) | (input) |
|  | Percentage |  |
| Inclement weather: % of Net | (input) | (input) |
| Contingency: % of Net | (input) | (input) |

## Key Assumptions

| Site Work Pattern/Roster | (input) Hours/Week | (input) Days/Week |
| --- | --- | --- |
| Non Work Days per Annum (RDO's, PH's, Xmas etc) | (input) Days p.a. | (input) weeks p.a. |

## Key Production Rates

| Significant Quantities & Productivities | Total Quantity | Units | Rate Per Day | Crew Size |
| --- | --- | --- | --- | --- |
| Activity / Material | (input) | (input) | (input) | (input) |
| Activity / Material | (input) | (input) | (input) | (input) |
| Activity / Material | (input) | (input) | (input) | (input) |

## Risks & Opportunities

| ID | Risk / Opport | Description | Proposed Mitigation |
| --- | --- | --- | --- |
| 7.11 | Risk | (input) | (input) |
| 7.12 | Risk | (input) | (input) |
| 7.14 | Opp | (input) | (input) |

## Summary Program

(insert high level 1 page program)

# Project Summary

## Location Map

Insert location map here

## Scope of Works

(input)

## Program Overview / Strategy

(delivery strategy – workfronts, zones, key drivers, proposed early works)

## Project Specific Issues

(input)

# Program Details

## Location & Identification

| Software Requirements |  |
| --- | --- |
| P6 Database |  |
| EPS Node |  |
| Project Id |  |
| Project Name |  |
| Data Date |  |
| Submission File |  |

## General Settings in P6

Default P6 settings are as follows:

Duration Type – Fixed Duration & Units

% Complete Type – Physical

Critical Total Float = 0 hours.

## Work Breakdown Structure

Describe how the WBS was developed

Provide Level 4 WBS at Appendix I

Align the WBS with the cost control structure in PCR

## Calendars.

The following calendars have been used:

## Allowable Working Hours.

Defined in the Project Brief as follows:

## Design

Scope and duration

Alignment with design partners

Understanding of client approvals / consent authorities requirements

## Procurement

Identify key items of equipment and lead times, crtical path lettings

## Construction Methodology

Briefly describe significant methods as highlighted in Item 1.4 above

# Key Assumptions

## Site Access and Establishments

Site establishmernt layout:

## Productivities

See Item 1.4 above for major activities

Add further detail for other activities

# Overall Labour Histogram

Refer to the histogram below, displaying anticipated resource requirements

Peak Labour force anticipated to be X JH, Y Subcontractor.

Self-perform manhours in schedule = ??

DJC manhours in estimate = ??

# Critical Path.

# Relevant Project Benchmarking

- Validation that SP’s / Key Dates are achievable from past projects

- Input comparable metric from past similar projects

# Inclement Weather Analysis

- Describe methodology

# Schedule Risk Analysis

- Describe methodology

# Contingency

- See Item in the Exec Summary

- How was this provision calculated?

# Appendix A – Summary Programme

# Appendix B – Inclement Weather Analysis

(standard insert)

# Appendix C - Schedule Risk Analysis

(software outputs)

# Appendix D – Project Calendars

XER Toolkit Printouts

# Appendix E – Critical Path

# Appendix F – Contractual Requirement Relevant to ‘Planning/Programming/Time’

# Appendix G - Table of Productivities

(is this required? Already included in the Exec Summary)

# Appendix H– Schedule Quality Checks

Provide copy of P6 Schedule Report and XER Toolkit Dashboard

Recommend as a minimum

- List of No Predecessors

- List of No Successors

- Activities with Excessive Total Float

- List of Constraints

- List of Long Duration Activities

# Appendix I – Work Breakdown Structure (Level 4)